DEVELOPMENT PLAN

Booky Editing Services — Full-Stack Web Application

Version 1.0  |  April 2025  |  GloverSoft Inc.

| Field | Detail |
| --- | --- |
| Document | Development Plan — Booky Editing Services |
| Version | 1.0 |
| Status | Approved — Ready for Execution |
| Developer | Adebayo Glover (GloverSoft Inc.) — sole developer |
| Repository | GitHub: booky ¦ Local: booky/ ¦ Docs: booky/docs/ |
| Stack | React JS • Express JS • PostgreSQL • CSS3 • Cloudinary • React Quill • Nodemailer |
| Branching Strategy | main (production) ¦ develop (staging) ¦ feature/* (work branches) |
| Total Estimated Effort | 28–38 working days (sole developer, full-time equivalent) |

# 1. Overview

This Development Plan defines the phased build order, task breakdown, effort estimates, and technical conventions for implementing the Booky Editing Services full-stack web application. It is the primary execution reference for GloverSoft Inc. during development.

The development follows a bottom-up, API-first approach: the database, backend, and API endpoints are built and tested before the frontend consumes them. This ensures the frontend is always built on stable, tested contracts.

All work is done in feature branches. Feature branches are merged to develop via pull request. develop is merged to main only after QA sign-off on staging.

# 2. Pre-Development Checklist

The following must be completed before a single line of application code is written:

| # | Item | Owner | Done? |
| --- | --- | --- | --- |
| 1 | GitHub repository 'booky' exists with main and develop branches protected | Adebayo Glover | ☐ |
| 2 | booky/docs/ folder exists and contains all SDLC documents | Adebayo Glover | ☐ |
| 3 | README.md created at repo root with project overview and setup instructions | Adebayo Glover | ☐ |
| 4 | PostgreSQL database provisioned on Neon / Supabase / Railway. Connection string obtained. | Adebayo Glover | ☐ |
| 5 | Cloudinary account created. Cloud name, API key, and API secret obtained. | Adebayo Glover | ☐ |
| 6 | Gmail App Password enabled and obtained for Nodemailer SMTP configuration | Adebayo Glover / Client | ☐ |
| 7 | server/.env file created locally with all required variables (see SDD §7.1) | Adebayo Glover | ☐ |
| 8 | server/.env.example file committed to repo documenting all variable names (no values) | Adebayo Glover | ☐ |
| 9 | Brand assets received from client: logo (SVG/PNG), founder photo (JPG/PNG) | Client | ☐ |
| 10 | Client testimonials (min 2) received and approved | Client | ☐ |
| 11 | WhatsApp Business number confirmed by client | Client | ☐ |
| 12 | Business email address for footer confirmed by client | Client | ☐ |
| 13 | Social media URLs confirmed by client | Client | ☐ |
| 14 | Node.js 20.x LTS installed locally. npm 10.x. Vite 5.x. Git. | Adebayo Glover | ☐ |

# 3. Development Phases & Task Breakdown

Phases are sequential. Do not proceed to the next phase until the current phase is complete and tested.

| Phase | Task | Est. Days | Deliverable / Done Criteria |
| --- | --- | --- | --- |
| Phase 0 | Project Scaffolding & Tooling |  |  |
| Phase 0 | Initialise Express server with folder structure per SDD §3.2 | 0.5 | server/ running on port 5000 |
| Phase 0 | Install all backend npm packages (see SDD §4.1) | 0.25 | package.json confirmed |
| Phase 0 | Configure dotenv, helmet, cors, express.json, express.urlencoded | 0.5 | GET /health returns 200 OK |
| Phase 0 | Configure Sequelize connection (db.js) with PostgreSQL pool settings | 0.5 | Sequelize.authenticate() succeeds |
| Phase 0 | Configure Cloudinary SDK (cloudinary.js) | 0.25 | Test upload succeeds to Cloudinary account |
| Phase 0 | Scaffold React app with Vite. Install React Router, Axios, React Hook Form, React Quill | 0.5 | npm run dev starts on port 5173 |
| Phase 0 | Create global.css with CSS variables for all brand colours, spacing, typography | 0.5 | Variables usable in all component CSS modules |
| Phase 0 | Commit initial scaffold to feature/setup branch → merge to develop | 0.25 | PR merged, develop branch clean |
| Phase 0 | PHASE 0 TOTAL |  | 3–4 days |
| Phase 1 | Database Models & Migrations |  |  |
| Phase 1 | Define all 7 Sequelize models per SDD §5 (Admin, PasswordResetToken, BlogPost, SiteSettings, AboutContent, Testimonial, QuoteSubmission) | 2 | Models defined with all fields, constraints, and associations |
| Phase 1 | Create Sequelize migrations for all tables | 1 | npx sequelize db:migrate runs without errors on clean DB |
| Phase 1 | Create seed file: initial admin user (hashed password), singleton settings row, singleton about_content row | 0.5 | Seed inserts successfully; admin can be used for login testing |
| Phase 1 | PHASE 1 TOTAL |  | 3–4 days |
| Phase 2 | Backend API — Auth & Security |  |  |
| Phase 2 | Build auth middleware (middleware/auth.js): JWT extraction, verification, req.user attachment | 0.5 | Middleware rejects invalid/missing tokens with 401 |
| Phase 2 | Build POST /api/auth/login: validate body, check credentials, bcrypt.compare, issue JWT, set httpOnly cookie | 1 | Correct credentials → 200 + token; wrong → 401; 5 failures → 423 locked |
| Phase 2 | Build POST /api/auth/logout: clear httpOnly cookie | 0.25 | Cookie cleared on response |
| Phase 2 | Build GET /api/auth/verify: validate cookie JWT, return user info | 0.5 | Valid cookie → 200 + user; invalid → 401 |
| Phase 2 | Build password reset flow: POST /api/auth/forgot-password + POST /api/auth/reset-password. Generate crypto token, store hash, send email via Nodemailer, validate on reset. | 1.5 | Email received with valid link; link expires after 1 hour; reuse rejected |
| Phase 2 | Apply express-rate-limit to login endpoint (5 attempts per 15-min window) | 0.25 | 6th request returns 429 Too Many Requests |
| Phase 2 | Test all auth endpoints with Postman / Thunder Client | 0.5 | All acceptance criteria for FR-AUTH-01 to FR-AUTH-12 pass |
| Phase 2 | PHASE 2 TOTAL |  | 4–5 days |
| Phase 3 | Backend API — All Resources |  |  |
| Phase 3 | Blog CRUD: GET /api/public/blogs (pagination), GET /api/public/blogs/:slug, GET/POST/PUT/DELETE /api/admin/blogs. Include slug generation (slugify + uniqueness check). Include Cloudinary cover image upload on POST/PUT. | 2 | All blog endpoints return correct data; slug unique constraint enforced; image upload/replace/delete works |
| Phase 3 | Settings: GET /api/public/settings, PUT /api/admin/settings, POST /api/admin/settings/logo, POST /api/admin/settings/photo. Include Cloudinary replace logic (delete old public_id before uploading new). | 1 | Settings update persists and GET reflects new values; old Cloudinary asset deleted on replace |
| Phase 3 | About Content: GET /api/public/about, PUT /api/admin/about | 0.5 | Content updates persist; public endpoint returns latest values |
| Phase 3 | Testimonials CRUD: GET /api/public/testimonials, POST/PUT/DELETE /api/admin/testimonials. Reorder via PUT with display_order. | 1 | Active testimonials returned in display_order; reorder persists |
| Phase 3 | Quote Form: POST /api/public/quote. Validate all 9 fields + honeypot. Handle multipart/form-data (Multer + Cloudinary for file). Save to DB. Send Nodemailer notification email. Apply rate limiting. | 1.5 | Submission saved to DB; email received; file upload to Cloudinary; honeypot rejects bots; rate limit works |
| Phase 3 | Quote Inbox: GET /api/admin/quotes (pagination + filter), GET /api/admin/quotes/:id (with signed Cloudinary URL), PUT /api/admin/quotes/:id/read | 0.5 | All submission data accessible; read toggle works; file download URL is accessible |
| Phase 3 | Implement global error handler middleware (middleware/errorHandler.js). Apply to all routes. | 0.5 | All errors return consistent JSON shape: { error: true, message, status } |
| Phase 3 | Add blog post HTML body sanitisation with isomorphic-dompurify before save | 0.25 | XSS payload in blog body is stripped on save |
| Phase 3 | Full API test pass with Postman / Thunder Client across all endpoints | 1 | All SRS v2.0 requirements for API endpoints verified |
| Phase 3 | PHASE 3 TOTAL |  | 8–10 days |
| Phase 4 | Frontend — Public Site |  |  |
| Phase 4 | Build shared layout: Navbar (with hamburger menu at 768px), Footer (dynamic from API), WhatsApp floating button, ProtectedRoute wrapper | 1 | Nav collapses on mobile; footer shows live settings data; WhatsApp button on all pages |
| Phase 4 | Build Home page: Hero, About Preview (with founder photo from API), Services Cards (6), Why Choose Us (4 values), Testimonials (from API), Final CTA Banner | 1.5 | All sections render; dynamic content loads from API; 2 CTA buttons in hero work |
| Phase 4 | Build About page: Founder Story (from API), Mission & Vision (from API), Brand Values (from API), CTA | 0.75 | All content loads dynamically from API; CTA links to /services and /contact |
| Phase 4 | Build Services page: All 6 services with alternating layout, full descriptions per SDD §11, individual CTAs, final CTA block | 1 | All 6 services displayed with correct content; CTAs link to /contact |
| Phase 4 | Build Testimonials page: Card grid (from API, ordered by display_order), CTA | 0.5 | Cards render from API; CTA links to /contact |
| Phase 4 | Build Contact/Quote page: React Hook Form with all 9 fields, validation, file upload, loading state, success/error states, honeypot field. POST to /api/public/quote. | 1.5 | All FR-C-01 to FR-C-16 acceptance criteria pass; form submits; success message shown |
| Phase 4 | Build Blog List page: Card grid with cover image, category, title, date, Read More link. Empty state. Pagination. | 0.75 | Published posts display; empty state shows when no posts; pagination works |
| Phase 4 | Build Blog Single Post page: Cover image, title, metadata, rich text body, sidebar, Back to Blog link. 404 for missing slug. | 0.75 | Post content renders as HTML; sidebar shows recent posts and CTA; 404 for bad slug |
| Phase 4 | Build 404 Not Found page | 0.25 | All unmatched routes render the 404 page with link to Home |
| Phase 4 | Apply all CSS3 styling per brand palette, typography, and design requirements. Full mobile responsive pass. | 2 | All pages match design brief; responsive across 320px to 2560px; PageSpeed 80+ mobile |
| Phase 4 | PHASE 4 TOTAL |  | 10–12 days |
| Phase 5 | Frontend — Admin Panel |  |  |
| Phase 5 | Build AuthContext and login flow: Login page, POST to /api/auth/login, store JWT in state + httpOnly cookie, redirect to /admin on success | 0.75 | Login works; JWT not in localStorage; redirect on success; error shown on failure |
| Phase 5 | Build ProtectedRoute: redirect to /admin/login if no token. Build Logout: clear cookie + state + redirect. | 0.5 | Direct URL to /admin redirects to login; logout clears session |
| Phase 5 | Build Admin Sidebar navigation with unread quote badge. Build Dashboard: stats summary + recent 5 quotes table + Quick Actions. | 1 | Sidebar persists across all admin routes; unread count badge updates; dashboard stats load |
| Phase 5 | Build Blog List (admin): table with Title, Status, Date, Edit/Delete actions. Filter by All/Published/Draft. | 0.75 | All posts listed; filter works; delete triggers confirmation; edit navigates to editor |
| Phase 5 | Build Blog Editor: title input (+ real-time slug preview), React Quill editor, category input, meta description (+ 160-char counter), cover image upload with preview, Save as Draft / Publish toggle. | 1.5 | New post saves to DB; React Quill content stored correctly; cover image uploads to Cloudinary; slug auto-generates |
| Phase 5 | Build Settings page: logo upload (preview + confirm), founder photo upload (preview + confirm), WhatsApp number, contact email, social links. Independent saves per section with success toast. | 1 | All settings update independently; logo/photo replace old Cloudinary assets; success toast shown |
| Phase 5 | Build About Editor: founder story textarea, mission/vision inputs, 4 value fields (label + description). Save button with success toast. | 0.75 | Saves persist; public About page reflects updates on reload |
| Phase 5 | Build Testimonials manager: list with drag-to-reorder, Add/Edit form, delete with confirmation. Saves order to API. | 1 | Drag reorder saves to DB and reflects on public site; CRUD all works |
| Phase 5 | Build Quote Inbox: paginated table, unread highlighting, filter All/Unread/Read, expandable row with all submission fields, manuscript download button, Mark as Read toggle. | 1 | All FR-QFM acceptance criteria pass; download link accessible |
| Phase 5 | Build password reset pages: Forgot Password form + Reset Password form. Connect to API endpoints. | 0.5 | Reset email received; link works; link expires correctly; reuse rejected |
| Phase 5 | PHASE 5 TOTAL |  | 8–10 days |
| Phase 6 | QA, Testing & Deployment |  |  |
| Phase 6 | Cross-browser testing: Chrome, Safari, Firefox, Edge (last 2 versions each) | 1 | AC-01 passes on all browsers |
| Phase 6 | Device testing: 375px (iPhone SE), 768px (iPad), 1440px (Desktop) | 0.5 | AC-02 passes on all tested viewports |
| Phase 6 | Google PageSpeed Insights run on all 5 public pages | 0.5 | AC-03: 80+ mobile, 90+ desktop on all pages |
| Phase 6 | Accessibility audit: WAVE or axe on all public pages | 0.5 | AC-11: 4.5:1 contrast ratio; no critical WCAG violations |
| Phase 6 | Full manual UAT pass against all Acceptance Criteria in SRS v2.0 §10 | 1.5 | All 19 acceptance criteria checked and documented |
| Phase 6 | Security checks: inspect DevTools for JWT in localStorage (must be absent); test direct /api/admin/* without token (must return 401); verify HTTPS on staging | 0.5 | AC-17, AC-18 pass |
| Phase 6 | Deploy backend to Render / Railway. Configure all environment variables in hosting dashboard. | 0.5 | API live at api.bookyediting.com; /health returns 200 |
| Phase 6 | Deploy frontend to Vercel. Configure VITE_API_URL to production API URL. | 0.5 | Public site live at bookyediting.com |
| Phase 6 | Run Sequelize migrations on production PostgreSQL database | 0.25 | All tables created; seed admin user exists |
| Phase 6 | End-to-end smoke test on production: submit quote form, receive email, log in to admin, view submission, publish blog post, verify on public site | 0.5 | All primary flows confirmed working in production |
| Phase 6 | Client UAT on staging: client reviews all pages and signs off on content accuracy (AC-19) | 1 | UAT sign-off document signed by client |
| Phase 6 | Handover: README updated with local setup, deployment instructions, environment variable documentation | 0.5 | README complete and accurate |
| Phase 6 | PHASE 6 TOTAL |  | 7–8 days |

# 4. Total Effort Estimate

| Phase | Description | Estimated Days |
| --- | --- | --- |
| Phase 0 | Project Scaffolding & Tooling | 3–4 days |
| Phase 1 | Database Models & Migrations | 3–4 days |
| Phase 2 | Backend API — Auth & Security | 4–5 days |
| Phase 3 | Backend API — All Resources | 8–10 days |
| Phase 4 | Frontend — Public Site | 10–12 days |
| Phase 5 | Frontend — Admin Panel | 8–10 days |
| Phase 6 | QA, Testing & Deployment | 7–8 days |
| TOTAL |  | 43–53 days (full-time equivalent, sole developer) |

Timeline estimate assumes: full-time focus, no significant scope changes, client-supplied content and assets delivered on schedule, and no major infrastructure issues. Part-time work will extend the timeline proportionally.

# 5. Branching & Commit Conventions

## 5.1 Branch Naming

| Branch Type | Format | Example |
| --- | --- | --- |
| Feature | feature/<short-description> | feature/auth-login |
| Bug Fix | fix/<short-description> | fix/quote-form-validation |
| Documentation | docs/<short-description> | docs/readme-update |
| Chore / Config | chore/<short-description> | chore/env-setup |

## 5.2 Commit Message Format

All commits follow this format: <type>(<scope>): <description>

| Type | When to Use | Example |
| --- | --- | --- |
| feat | New feature added | feat(auth): implement JWT login with httpOnly cookie |
| fix | Bug fixed | fix(quote-form): validate honeypot field server-side |
| chore | Config or tooling change | chore(deps): install express-rate-limit |
| docs | Documentation update | docs(readme): add local setup instructions |
| style | CSS / formatting only | style(navbar): fix hamburger z-index on mobile |
| refactor | Code refactored, no behaviour change | refactor(blog): extract slug service to utils |
| test | Test added or updated | test(auth): add Postman collection for login flow |

# 6. Definition of Done

A task is not complete until ALL of the following are true:

- Feature works as specified in the SRS v2.0 requirement it implements

- All edge cases handled: empty state, error state, loading state

- API endpoints return correct HTTP status codes for all scenarios

- No console errors in browser DevTools

- No errors in Express server logs

- Mobile responsive: tested at 375px and 768px viewports

- CSS: no inline styles in JSX; all styles in CSS Modules or global.css

- No sensitive data (API keys, passwords, JWT) exposed in client-side code or git history

- Feature branch is clean (no debug code, no TODO comments left open)

- PR merged to develop with a clear description of what was built

# 7. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Client delays in providing assets (logo, photos, testimonials, WhatsApp number) | High | Medium — blocks frontend content phases | Begin with placeholder assets. Document all outstanding items in Pre-Development Checklist. |
| React Quill 2.x compatibility issues with React 18 strict mode | Medium | Medium — may require workaround or wrapper | Test early in Phase 5. If unresolvable, evaluate react-quill fork or Quill.js direct integration. |
| PostgreSQL connection instability on free-tier hosting | Medium | High — app non-functional if DB unreachable | Configure Sequelize connection pooling. Implement health check endpoint. Use paid tier if stability is critical. |
| Gmail SMTP rate limits affecting email delivery | Low | Medium — quote notifications delayed | Monitor send volume. App Password has higher limits than OAuth. Can upgrade to SendGrid if needed. |
| Cloudinary free tier storage limits | Low | Low — only affects high volume of assets | Monitor usage. Free tier is 25 GB storage — sufficient at launch. |
| Scope creep from client requesting additional features during development | Medium | High — delays launch | All new requests go through formal Change Request process. Post-launch roadmap clearly communicated to client. |

# 8. Approval

| Role | Name / Organisation | Signature / Date |
| --- | --- | --- |
| Lead Developer & CEO | Adebayo Glover — GloverSoft Inc. |  |
| Product Owner | Booky Editing Services |  |

© 2025 Booky Editing Services. Development Plan v1.0. Prepared by GloverSoft Inc. Confidential — Not for Distribution.